## SCHEDULE
ACTIVITY SCHEDULE I2
Levels		TAREAS	RESOURCES				WEEKS
					WEEK 1					WEEK 2					WEEK 3					WEEK 4
			Alba	Ivan	Eva	Jiri	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20
0	1	Weekly Coordination Meeting	X	X	X	X
R1	1	Game: make the data structure opaque				X
R2	1	Inventory: data structure	X
R2	2	Inventory: functions create, destroy		X
R2	3	Inventory: functions get, set	X	X
R2	4	Inventory: function print	X
R2	5	Inventory: inventory_test		X
R2	6	Inventory: Document	X	X
R3	1	Modify player	X
R3	2	Player: add functions	X
R3	3	Player: player_text		X
R4	1	GameReader: load player		X
R5	1	Link: data structure				X
R5	2	Link: functions create, destroy				X
R5	3	Link: functions get, set				X
R5	4	Link: function print				X
R5	5	Link: link_test				X
R5	6	Link: Document				X
R6	1	GameReader: load links				X
R6	2	Modify space_test				X
R7	1	Modify visualition with links				X
R8	1	Modify data file			X
R9	1	Command: move			X
R10	1	Modify Object			X
R10	2	Command: examine			X
R10	3	Object: object_test			X
R11	1	Modify inspect			X
R11	2	Modify space			X
R12	1	Modify all necessary modules	X
R13	1	Modify take, drop		X
R14	1	Command file I2 style		X
R14	2	Command file I3 style	X
R15	1	Meeting minutes	X	X	X	X
R15	2	Gantt diagrams	X	X	X	X
R16	1	Modify headers	X	X	X	X
R16	2	Doxygen documentation				X
R17	1	Modify makefile				X
R18	1	Unit testing	X	X	X	X
R19	1	Debugging errors	X	X	X	X
20	1	General review	X	X	X	X
21	1	Submission	X	X	X	X

## RESOURCES
RESOURCES IDENTIFICATION
R1	Name1
R2	Name2