## SCHEDULE
ACTIVITY SCHEDULE I2
Levels		TAREAS	RESOURCES		WEEKS
					WEEK 1					WEEK 2					WEEK 3
			R1	R2	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15
0	1	Weekly Coordination Meeting	X	X
R1	1	Set: data structure
R1	2	Set: functions create, destroy
R1	3	Set: functions add, del
R1	4	Set: function print
R1	5	Set: set_test
R1	6	Set: Document
R2	1	Space with Set: modify struct
R2	2	Space with Set: modify functions
R2	3	Space with Set: add functions
R2	4	Modify space_test
R2	5	Space: Document
R3	1	Die: data structure
R3	2	Die: functions create, destroy
R3	3	Die: functions get, set, roll
R3	4	Die: function print
R3	5	Die: die_test
R3	6	Die: Document
R4	1	Modify other modules using R1, R2 y R3
R5	1	Add 4 objects to data.dat
R6	1	GameReader: load objects
R7	1	Command roll
R8	1	Command left
R8	2	Command right
R9	1	Modify command take
R10	1	Space: add field gdesc
R10	2	Space: modify create, destroy, print
R10	3	Space: add get, set for the field gdesc
R10	4	Modify space_test
R11	1	New, complete data file
R12	1	GameReader: modify load_spaces
R13	1	Visualization: space graphic descripction
R13	2	Visualization: object location
R13	3	Visualization: several objects in a space
R13	4	Visualization: player's objects
R13	5	Visualization: last roll of the die
R13	6	Visualization: last executed command
R14	1	LOG file
15	1	Makefile	X	X
16	1	Debugging errors	X	X
17	1	General review
18	1	Submission

## RESOURCES
RESOURCES IDENTIFICATION
R1	Name1
R2	Name2