## SCHEDULE
ACTIVITY SCHEDULE I1
Levels		TAREAS	RESOURCES		WEEKS
					WEEK 1					WEEK 2					WEEK 3
			R1	R2	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15
0	1	Weekly Coordination Meeting	X	X
1	1	Makefile	X	X
2	1	Seed-src: Fix warnings and understand code	X	X
2	2	Seed-scr: Document		X		R2	R2	R2	R2
2	3	Seed-scr: Programming Style		X					R2
3	1	Create the GameReader module	X			R1	R1	R1
3	2	GameReader: Document	X			R1	R1	R1
4	1	Modify Game with GameReader functions	X					R1
5	1	Object: data structure	X					R1
5	2	Object: functions create, destroy	X					R1	R1
5	3	Object: functions get, set	X					R1	R1
5	4	Object: function print	X					R1
5	5	Object: Document	X					R1	R1	R1
6	1	Player: data structure		X					R2
6	2	Player: functions create, destroy		X					R2	R2
6	3	Player: functions get, set		X					R2	R2
6	4	Player: function print		X					R2
6	5	Player: Document		X					R2	R2	R2
7	1	Modify Game	X					R1	R1	R1
7	2	Modify Space	X					R1	R1
7	3	Modify other modules?	X					R1
8	1	Command take		X					R2	R2
8	2	Command drop		X					R2	R2
9	1	Data file		X					R2
10	1	Modify game_loop?	X					R1
11	1	Debugging errors	X	X
12	1	General review	X	X
13	1	Submission	X					R1

## RESOURCES
RESOURCES IDENTIFICATION
R1	Name1
R2	Name2