## SCHEDULE
ACTIVITY SCHEDULE I2
Levels		TAREAS	RESOURCES		WEEKS
					WEEK 1					WEEK 2					WEEK 3
			Eva	Jiri	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15
0	1	Weekly Coordination Meeting	X	X
R1	1	Set: data structure	X
R1	2	Set: functions create, destroy	X
R1	3	Set: functions add, del	X
R1	4	Set: function print		X
R1	5	Set: set_test		X
R1	6	Set: Document	X
R2	1	Space with Set: modify struct		X
R2	2	Space with Set: modify functions		X
R2	3	Space with Set: add functions		X
R2	4	Modify space_test	X
R2	5	Space: Document		X
R3	1	Die: data structure		X
R3	2	Die: functions create, destroy		X
R3	3	Die: functions get, set, roll		X
R3	4	Die: function print	X
R3	5	Die: die_test		X
R3	6	Die: Document		X
R4	1	Modify other modules using R1, R2 y R3	X
R5	1	Add 4 objects to data.dat	X
R6	1	GameReader: load objects	X
R7	1	Command roll	X
R8	1	Command left		X
R8	2	Command right		X
R9	1	Modify command take	X
R10	1	Space: add field gdesc	X
R10	2	Space: modify create, destroy, print	X
R10	3	Space: add get, set for the field gdesc		X
R10	4	Modify space_test		X
R11	1	New, complete data file		X
R12	1	GameReader: modify load_spaces	X
R13	1	Visualization: space graphic descripction	X
R13	2	Visualization: object location	X
R13	3	Visualization: several objects in a space	X
R13	4	Visualization: player's objects		X
R13	5	Visualization: last roll of the die		X
R13	6	Visualization: last executed command		X
R14	1	LOG file		X
15	1	Makefile	X	X
16	1	Debugging errors	X	X
17	1	General review
18	1	Submission

## RESOURCES
RESOURCES IDENTIFICATION
R1	Name1
R2	Name2