## SCHEDULE
ACTIVITY SCHEDULE I1
Levels		TAREAS	RESOURCES		WEEKS
					WEEK 1					WEEK 2					WEEK 3
			R1	R2	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15
0	1	Weekly Coordination Meeting	X	X
1	1	Makefile	X		R1
2	1	Seed-src: Fix warnings and understand code	X		R1
2	2	Seed-scr: Document		X					R2	R2	R2	R2
2	3	Seed-scr: Programming Style	X	X
3	1	Create the GameReader module		X		R2	R2
3	2	GameReader: Document		X		R2	R2
4	1	Modify Game with GameReader functions		X			R2
5	1	Object: data structure	X			R1
5	2	Object: functions create, destroy	X			R1
5	3	Object: functions get, set	X			R1
5	4	Object: function print	X			R1
5	5	Object: Document	X					R1	R1	R1
6	1	Player: data structure	X			R1
6	2	Player: functions create, destroy	X			R1
6	3	Player: functions get, set	X			R1	R1
6	4	Player: function print	X			R1
6	5	Player: Document	X					R1	R1	R1
7	1	Modify Game		X			R2
7	2	Modify Space		X			R2
7	3	Modify other modules?		X			R2
8	1	Command take		X					R2
8	2	Command drop	X					R1
9	1	Data file	X					R1
10	1	Modify game_loop?		X					R2
11	1	Debugging errors	X	X
12	1	General review	X	X
13	1	Submission	X					R1

## RESOURCES
RESOURCES IDENTIFICATION
R1	Name1
R2	Name2