## SCHEDULE
ACTIVITY SCHEDULE I2
Levels		TAREAS	RESOURCES				WEEKS
					WEEK 1					WEEK 2					WEEK 3
			Alba	Ivan	Eva	Jiri	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15
0	1	Weekly Coordination Meeting	X	X	X	X
R1	1	Modify space data structure	X
R1	2	Space: functions get, set, print for boolean	X
R2	1	Modify Space - add up, down	X
R2	2	Space: add move up, down	X
R3	1	Space: detailed description	X
R4	1	Command: modify inspect	X
R5	1	Object: movable				X
R5	2	Object: dependency				X
R5	3	Object: open				X
R5	4	Object: illuminate				X
R5	5	Object: turnedon				X
R6	1	Add functions for taking object				X
R7	1	Command: turnon, turnoff				X
R8	1	Command: open link				X
R9	1	Modify data files		X
R10	1	Create adventure	X	X	X	X
R11	1	Create user guide	X	X	X	X
R12	1	GameManagement module			X
R12	2	GameManagement: save, load game state			X
R13	1	Command: save, load			X
R14	1	Dialogue		X
R15	1	GameRules		X
R16	1	Modify necessary modules	X	X	X	X
R16	2	Implement tests	X	X	X	X
R16	3	Modify makefile	X	X	X	X
R16	4	Debugging errors	X	X	X	X
R16	5	Document	X	X	X	X
R16	6	Manage project	X	X	X	X

## RESOURCES
RESOURCES IDENTIFICATION
R1	Name1
R2	Name2